## Feuil1
Valais Eat logbook
Hugo Vouillamoz & Benjamin Morel
Total estimate of time spent on the projet : ~70-80 hours
Problems encountered :
- We noticed while making the web application that we lacked methods in the DAL. We hadn't thought about everything we needed at the start, it wasn't necessarily easy. We therefore had to take time to create them as well as the interfaces.
- We created different models because we needed data from multiple tables including id's.
- What we did not know how to do, we went to look for the answers in the course (exercises carried out in class), or on the internet
- Overall we didn't have too many problems and really enjoyed working on this project :)
|  | September | October |  |  |  | November |  |  |  |  | December |  |  |  | January
Tasks | Person responsible | 2021-09-28 | 2021-10-03 | 2021-10-12 | 2021-10-19 | 2021-10-26 | 2021-11-02 | 2021-11-07 | 2021-11-16 | 2021-11-23 | 2021-11-30 | 2021-12-07 | 2021-12-14 | 2021-12-21 | 2021-12-28 | 2022-01-04 | 2022-01-09
Database diagram | Hugo + Benjamin | bar: 2021-09-28
First tables + modelisation | bar: 2021-09-28
First deliverable
Database creation | Hugo + Benjamin | bar: 2021-10-12
Creation of the git lab | bar: 2021-10-12
Creation of the project | bar: 2021-10-12
Initial commit + creation of dev branch | bar: 2021-10-12
Creation of a table script | Benjamin | bar: 2021-10-19 to 2021-10-26
Creation of a data script | bar: 2021-10-19 to 2021-11-02
Creation of the DAL + BLL interfaces | Hugo + Benjamin | bar: 2021-10-26 to 2021-11-02
Adding todo for better organization | bar: 2021-10-26
Method to authentificate the user to connect | Hugo | bar: 2021-10-26 to 2021-11-02
Method to add users + logins | Hugo | bar: 2021-11-02
Changes to structure DAL + BLL | Hugo + Benjamin | bar: 2021-11-02
Second deliverable
Creation of the web application | Hugo + Benjamin | bar: 2021-11-16
Creation of the first views | Benjamin | bar: 2021-11-16 to 2021-11-23
Adding new methods | Hugo + Benjamin | bar: 2021-11-16 to 2021-12-21
Creation of the different layouts | Benjamin | bar: 2021-12-14
Login page | Hugo | bar: 2021-11-30 to 2021-12-14
Adding images | Hugo + Benjamin | bar: 2021-12-21
Creation of chart details | Hugo | bar: 2021-12-14 to 2021-12-28
Creation of staff + restaurant page + admin page | Hugo + Benjamin | bar: 2021-12-28 to 2022-01-04
Creation of contact page | Benjamin | bar: 2021-12-28 to 2022-01-04
Creation of comments + reviews | Hugo | bar: 2021-12-28 to 2022-01-04
Adding small new features | Hugo + Benjamin | bar: 2022-01-04
Final check + preparation of the presentation | bar: 2022-01-04
Final deliverable